## Sheet1
Personal Tracker Application Work Breakdown Structure
WBS# | Task Name | WBS Description | Done? | Comments/Results
1 | App Layout |  | FALSE
1.1 | Choose Colors | Choose 3-4 colors, at least one very light and one very dark, to use in the app design. | TRUE | 7D0147 (Tyrian Purple), 1F5673 (Lapis Lazuli), 568259 (Fern Green), E3DCC2 (Pearl)
1.2 | Create Wireframes | Create 1:2 designs for each part of the app | FALSE
1.2.1 | Dashboard Wireframe | Include title/logo, verse of the day, search by date, links to each category, a button to add a new entry to each category | TRUE
1.2.2 | Task List Wireframe | Include smaller logo and "Task List" title, the date, a checklist for each item, a button to add a new task, keep the other two category links at the bottom | TRUE
1.2.3 | Task Form Wireframe | (pop up?) A simple form that verifies the date and adds the task decription | TRUE
1.2.4 | Meal List Wireframe |  | TRUE
1.2.5 | Meal Form Wireframe |  | TRUE | Combined by "save" button with meal list
1.2.6 | Prayer Request Form Wireframe |  | TRUE
1.2.7 | Prayer Request List Wireframe |  | TRUE
1.2.8 | Praise Report List Wireframe |  | TRUE
1.2.9 | Praise Report Form Wireframe |  | FALSE
1.3 | Final Design Approval | Review all wireframes and upload to Git | FALSE
2 |  |  | FALSE
2.1 |  |  | FALSE
2.1.1 |  |  | FALSE
2.1.2 |  |  | FALSE
3 |  |  | FALSE
3.1 |  |  | FALSE
3.2 |  |  | FALSE
4 |  |  | FALSE
4.1 |  |  | FALSE
4.2 |  |  | FALSE
4.3 |  |  | FALSE
5